## execution log
Records | Count | %Value
Total No. of test cases
No. of test cases executed
No. of test cases Skipped
No. of test cases pending
No. of test cases passed
No. of test cases Failed

## defect report
DF_ID | Reporting Date | Product Name | Product Version | Module | Sub Module | Type of Defect | Phase In Which you Found that | Summary of defect | Step to reproduce | Severity | Priority | Status | Reported by | Assigned to
DF_01 | 14/08/2022 | ZOOM | 5.11.3 | Sign In/up | Sign in with other options | Functional | Unit Testing | Unable to sign in when linking through Google account or SSO | 1. Click on Sign In option | High | High | open | Raj | Tejashri
2. Click on SSO or Google
DF_02 | 14/08/2022 | ZOOM | 5.11.3 | Join Meeting | Personal Link Name | Functional | Unit Testing | Unable to join meeting using personal link name | 1. Click on Join Meeting | Medium | High | open | Manasi | Rohan
2. Join Meeting using Personal Link Name
DF_03 | 15/08/2022 | ZOOM | 5.11.3 | Screen Sharing | Share Sound | Functional | System Testing | At the time of screen sharing using sound, Participants are not able to hear the sound | 1. Click on Share Screen | High | High | new | Manasi | Shruti
2. Click on Share Sound Box
DF_04 | 16/08/2022 | ZOOM | 5.11.3 | Chat | emoji | Non -Functional | System Testing | Cannot send multiple emoji's in a single click | 1. Click on Chat | Low | low | new | Raj | Anisha
2. Click on emoji
3. Select emoji
DF_05 | 17/08/2022 | ZOOM | 5.11.3 | Record | NA | Functional | System Testing | Recording stops automatically after a specific time interval | 1. Click on Recording | Medium | Medium | new | Manasi | Abhijeet
2. Recording starts(you will get notified)
DF_06 | 17/08/2022 | ZOOM | 5.11.3 | Chat | File sharing | Non -Functional | Smoke Testing | Unable to share Files in chat from local Drive/Computer | 1. Click on Chat | Medium | Medium | new | Raj | Siddhant
2. Click on File sharing
3. Select Local Drive/Computer option
DF_07 | 17/08/2022 | ZOOM | 5.11.3 | Participant | Unmute | Non -Functional | Unit Testing | Host is unable to unmute the participants. | 1. Click on Participant | High | Medium | new | Raj | Ishita
2. Click on options.
3. Click Unmute participants
DF_08 | 18/08/2022 | ZOOM | 5.11.3 | Schedule | Calender | Functional | Integration Testing | Not able to schedule meeting using outlook option | 1. Click on Schedule | low | low | new | Manasi | Tejashri
2. In Calender section
3. Select Outlook
DF_09 | 19/08/2022 | ZOOM | 5.11.3 | Microphone | NA | Functional | Integration Testing | Microphone is not compatible to zoom | 1. Click on Microphone Symbol | medium | High | new | Manasi | Anisha
DF_10 | 20/08/2022 | ZOOM | 5.11.3 | Participant | NA | Functional | Unit Testing | In a meet of 1000 people only 200 participants are able to join. | 1. Click on Join Meet | High | High | new | Raj | Ayush